## Sheet1
Construction Project | Risk | Probability (1-5) | Impact (1-5) | Total Risk Score (=P * I) | Mitigation Strategy | Owner
| Theft of construction material | 3 | 4 | 12 | Hire a security firm to install cameras and deterant to the construction site before materials are brought in | John - Security Manager
| Missing project deadlines | 3 | 2 | 6 | Effective schedule planning and ensuring a open communication between the employees managers and workers can reduce the impact of this risk. | Alicia - Project Manager
| Mass project confusion | 1 | 5 | 5 | With an effective project plan and properly explaining the requirements and deliverables along with the transition stages after each stage is completed. | Alicia - Project Manager
| Failed an integral project stage | 2 | 5 | 10 | Using proper checks and balances during the construction process for each stage and integrating checks during the process. | Garret - Construction Manager
| Legal issues due to permits or licencing | 2 | 4 | 8 | This can be mitigated by creating a task at each stage to assess the resources, their respective licences and permits aswell as consulting existing constuction documents for permit issues. | Steven - Lead Architect
|  | 5 | 5 | 20
|  | 1 | 1 | 1